## Metadata
Name | CreatedAt | UpdatedAt
AI Dashboard Development | 2026-02-11T00:42:55.383Z | 2026-02-11T00:42:55.404Z

## Source
# Project: AI Dashboard Development
## Sprint Configuration
- Duration: 4 weeks
- Start Date: 2024-01-15
- Active Sprint: Sprint 1
## People
- Alice: Frontend Development, UI/UX Design
- Bob: Backend Development, Database Management
- Carol: Machine Learning Model Development, Data Analysis
## Timeline
- Sprint 1: (2024-01-15 to 2024-01-28) [50%] {actual: 2024-01-15 to 2024-01-28} Initial setup and design
- Sprint 2: (2024-01-29 to 2024-02-11) [50%] {actual: 2024-01-29 to 2024-02-11} Development and integration
## Tasks
- Set up project repository and initial framework (Alice) {Sprint 1} <Initial setup> [todo]
- Design wireframes for the dashboard (Alice) {Sprint 1} <UI/UX Design> [todo]
- Set up backend server and database (Bob) {Sprint 1} <Initial setup> [todo]
- Define data requirements and preprocessing steps (Carol) {Sprint 1} <Data Analysis> [todo]
- Implement frontend components (Alice) {Sprint 2} [todo]
- Develop API for data retrieval (Bob) {Sprint 2} [todo]
- Train machine learning model (Carol) {Sprint 2} [todo]
- Integrate frontend with backend and ML model (Alice, Bob, Carol) {Sprint 2} <Final integration> [todo]

## People
Name | Responsibilities
Alice | Frontend Development, UI/UX Design
Bob | Backend Development, Database Management
Carol | Machine Learning Model Development, Data Analysis

## Tasks
Title | Assignee | Status | Sprint | Remarks
Set up project repository and initial framework | Alice | todo | Sprint 1 | Initial setup
Design wireframes for the dashboard | Alice | todo | Sprint 1 | UI/UX Design
Set up backend server and database | Bob | todo | Sprint 1 | Initial setup
Define data requirements and preprocessing steps | Carol | todo | Sprint 1 | Data Analysis
Implement frontend components | Alice | todo | Sprint 2
Develop API for data retrieval | Bob | todo | Sprint 2
Train machine learning model | Carol | todo | Sprint 2
Integrate frontend with backend and ML model | Alice, Bob, Carol | todo | Sprint 2 | Final integration

## Timeline
Label | Description | Percentage | StartDate | EndDate | ActualStartDate | ActualEndDate
Sprint 1 | Initial setup and design | 50 | 2024-01-15 | 2024-01-28 | 2024-01-15 | 2024-01-28
Sprint 2 | Development and integration | 50 | 2024-01-29 | 2024-02-11 | 2024-01-29 | 2024-02-11

## SprintConfig
Duration | StartDate
4 | 2024-01-15

## GanttChart
GANTT CHART | Planned |  | Actual |  | On track | Behind
|  | Jan 15 |  | Jan 22 |  | Jan 29 | Feb 5 | Feb 12 | Progress
Sprint 1 | [8 empty] | 50% on time
Sprint 2 | [8 empty] | 50% on time

## TimelineUI
Label | Description | Progress % | Planned Start | Planned End | Actual Start | Actual End | Variance (days) | Status
[Sprint Config] |  |  | 2024-01-15 |  |  |  |  | Duration: 4wk ¦ Active: Sprint 1
Sprint 1 | Initial setup and design | 50 | 2024-01-15 | 2024-01-28 | 2024-01-15 | 2024-01-28 | 0 | On time
Sprint 2 | Development and integration | 50 | 2024-01-29 | 2024-02-11 | 2024-01-29 | 2024-02-11 | 0 | On time